PROJECT ASTRA

Prototype Production Pipeline

Four parallel tracks across four phases  ·  ~15–17 weeks realistic timeline  ·  Grant-ready deliverable

Four Principles That Drive This Sequencing 1. Art direction is the gating dependency — nothing in Phase 1 can start until it's locked. 2. Parallel tracks reduce calendar time, not effort. Code refactor, world bible, and game design run alongside early art work. 3. Realistic ceiling is 2–3 simultaneous external collaborators. You can't manage six hires while developing. 4. Build the trailer-ready 60 seconds first, polish around it. Don't push everything to 70% and panic-polish at the end.

PHASE 0 · Pre-Production Lock-In (Weeks 1–3) Lock every decision that downstream work depends on. Mostly your time, ending with paid art-direction style tests.

| CODE / TECH You • Week 3 | ART You + Concept Artist • Weeks 1–3 | GAME DESIGN You • Weeks 1–3 | NARRATIVE You • Week 2 |
| --- | --- | --- | --- |
| Refactoring scope plan 3–5 days • Solo - Decide what to refactor vs. leave alone - Don't gold-plate — VS will need another pass - Goal: enable rapid content iteration | Reference gathering 1 week • Solo - Pinterest / PureRef board, 50+ images - SRPG palette studies + mythology iconography - Sprite size benchmarks (GBA FE reference) Mood board commission 1 week • Concept artist • ₹15k–40k - 2–3 paid style test pieces - Test top 2 candidates before locking Art direction lock + style guide 3–5 days • You + artist - 1-page bible: palette, silhouette, shading rules - Do/don't examples for downstream artists - GATING DEPENDENCY for all Phase 1 art | Unit roster 1 week • Solo - 5 player units with distinct class identities - 5 enemy units + 1 boss + 2 ally (optional) - Stats, abilities, role per unit 60-min user workflow design 1.5 weeks • Solo - Full prototype experience map - Title → tutorial → encounter → close - Define every player decision point Hero map encounter + tutorial flow 1 week • Solo - Defensive + offensive objectives - Tutorial integrated, not bolted on - One signature twist (rescue / chokepoint / convert) | World bible outline 1 week • Solo - Factions, themes, mythology framing - Main cast bios (motivations, voice) - Outline level only — v1 expansion in Phase 1 |

PHASE 1 · Anchor Asset Creation (Weeks 3–10) Longest phase. All four tracks run in parallel. Pixel art is critical path — everything else flexes around it.

| CODE / TECH You • ~4 weeks | ART Pixel + Portrait + UI Artists • ~7 weeks | GAME DESIGN You • Rolling | NARRATIVE Writer (or You) • ~3 weeks |
| --- | --- | --- | --- |
| Refactoring Layer 1 2.5 weeks • Solo - Touch only what blocks content iteration - Stable build > clean code at this stage Asset integration plumbing 1 week • Solo - Sprite pipeline + animation controller - Dialogue system hooks - Front-load this — assets land in week 5–6 Build pipeline 3–5 days • Solo - Reliable .exe / itch link output - No crashes, hangs, desyncs - Basic settings (res, audio, exit) | Environment art 2.5 weeks • Pixel artist • Start here (gates map composition) - Tileset for hero map biome (1.5 wks) - Hero map composition — you assemble (1 wk) - Battle backgrounds per terrain type Combat sprites + animations 5–6 weeks • Pixel artist • CRITICAL PATH - 5 player units — full anim sets: idle/move/attack/ability/hit/death (2.5 wks) - 5 enemy units — reuse skeleton from players (2 wks) - 1 boss sprite — extra polish, key art moment (1 wk) - 2 ally sprites — OPTIONAL, first to cut if slipping (1 wk) Portraits 5 weeks • Portrait artist - 5 main cast portraits, 2–3 expressions each (3 wks) - Boss portrait at key art quality (1 wk) - 3–4 generic enemy portraits (1 wk) UI + branding 3 weeks • UI designer or You - HUD, menus, dialogue boxes, character screens - Title screen + logo (grant first impression) - Pause / options / settings Weapon + item icons 3–5 days • Pixel artist - Lowest priority — can be last | Encounter detailed design Rolling • Solo - Spawn waves, scripted events - Win/loss state, defensive + offensive beats - Damage formulas + stat curves end-to-end Class identity design Rolling • Solo - Each unit type: distinct feel, not just stats - Define signature ability per class Tutorial encounter design Rolling • Solo - 4th-wall narration drives instruction - KISS — clarity > polish Note: most game design execution happens in Phase 2 iteration. Phase 1 is design-on-paper while art is being built. | Full prototype dialogue 2 weeks • Writer or You - 4th-wall narration to grant board - Pre-battle, mid-battle, post-battle beats - Set player expectations through narration World bible v1 expansion 1 week • Writer or You - From outline → working reference doc - Character voice samples for consistency If hiring a writer: brief them in week 3 so deadlines come from outside. Procrastination risk on weakest pillar. |

PHASE 2 · Integration & Iteration (Weeks 9–14) Stitch art into the build, iterate the encounter until it's genuinely fun. This is where the prototype earns its grant pitch.

| CODE / TECH You • ~4 weeks | ART You + Optional Composer • ~1.5 weeks | GAME DESIGN You + Playtesters • ~3.5 weeks | NARRATIVE You • ~1 week |
| --- | --- | --- | --- |
| Sprite + portrait integration 2 weeks rolling • Solo - Begins as art lands, runs in parallel UI implementation 2 weeks • Solo - Wire all menus, HUD, dialogue boxes Tutorial implementation 1.5 weeks • Solo - Trigger logic, contextual prompts Dialogue scripting in-engine 1 week • Solo - Hook writer's text into dialogue system Bug fix + stability 1.5 weeks • Solo - No crashes/hangs/desyncs in handout build | Audio pass 1.5 weeks • You + optional composer - AI-generated music (Suno / Udio) - Library SFX for combat + UI - Optional: 1 commissioned signature track Late-arriving art assets land here too — anything pushed from Phase 1 by 1–2 weeks. | Encounter balancing 2 weeks • You + 3–5 playtesters - Difficulty tuning across both objectives - Stat / damage formula adjustments Fun pass iteration 2 weeks (overlaps balancing) • You + testers - The encounter must be genuinely fun - Iterate until testers want more, not less - Use dev Discord for free playtest rounds This is where the prototype earns its grant pitch. Don't shortchange it. | Dialogue polish 1 week • Writer or You - Tighten lines based on playtest reactions - Pacing fixes — cut anything that drags |

PHASE 3 · Grant Deliverables (Weeks 13–16) Package the prototype for grant submission. Some items can start as early as Week 5.

| CODE / TECH You • ~1 week | ART You + Designer • ~2 weeks | GAME DESIGN You • ~2 weeks | NARRATIVE You • ~1.5 weeks |
| --- | --- | --- | --- |
| Final stable build 3–5 days • Solo - Handout .exe / itch link - Locked version for grant submission - No last-minute commits during pitch window | Pitch deck design 1.5 weeks • You + optional designer - 12–15 slides - Visual-first, minimal text per slide Mood board / concept art board 3 days • You + artist - Can start as early as Week 5 30-sec teaser cut 3–5 days • You + editor • OPTIONAL - Strong-to-have for social before submission | Gameplay video (2–4 min) 1.5 weeks • Solo - Anchor encounter on hero map - Show the Indian mythology angle in first 15 sec - Record after build is stable, not before One-page game design summary 3 days • Solo - Pitch + key mechanics + USP - Often the only thing read carefully | Elevator pitch 1 week iteration • Solo - One-sentence + one-paragraph versions - Test on people who don't know the project |

Hiring Plan

P1 = Critical hire  ·  P2 = Strongly recommended  ·  P3 = Nice-to-have / DIY-able

| Role | Priority | Engagement | India Rate Range | Estimated Total |
| --- | --- | --- | --- | --- |
| Lead Pixel Artist Single most important hire | P1 | 6–7 weeks contract | ₹600–1,800/hr or ₹10k–30k/character | ₹2,50,000 – ₹5,50,000 |
| Portrait Artist Indian myth iconography literacy | P1 | 4–5 weeks, per-portrait | ₹4,000–15,000 per portrait set | ₹80,000 – ₹2,00,000 |
| Narrative Designer / Writer Unblocks your weakest pillar | P2 | Project-based, 2–3 weeks | ₹3–15/word or ₹50k–1.2L flat | ₹50,000 – ₹1,20,000 |
| UI/UX Designer Skip if you can iterate yourself | P3 | Project-based, 2–3 weeks | ₹40k–1.2L project flat | ₹40,000 – ₹1,20,000 |
| Composer 1 signature track for trailer | P3 | One-off commission | ₹15,000–60,000 per track | ₹15,000 – ₹60,000 |
| Concept Artist Phase 0 only — often same as portrait artist | P3 | 2–3 reference pieces | ₹15,000–40,000 total | ₹15,000 – ₹40,000 |

Budget Tiers

Indian freelance market estimates. Eastern European / SE Asian rates similar; Western rates 2–3× higher. Get quotes before locking budget.

| Tier | Pixel Art | Portraits | Writer | UI | Music | Concept | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Lean | ₹2,50,000 | ₹80,000 | DIY | DIY | AI | ₹15,000 | ~₹3,45,000 ($4.1k) |
| Comfortable | ₹3,50,000 | ₹1,20,000 | ₹70,000 | ₹50,000 | ₹25,000 | ₹25,000 | ~₹6,40,000 ($7.7k) |
| Premium | ₹5,50,000 | ₹2,00,000 | ₹1,20,000 | ₹1,20,000 | ₹60,000 | ₹40,000 | ~₹10,90,000 ($13k) |

Critical Path — The Sequence That Gates Everything Art direction lock → tileset → hero map → player sprite integration → encounter iteration → gameplay video. If any link slips, everything downstream slips. All other tracks (portraits, narrative, audio, code refactor) can flex around this spine.

Top 5 Risks & Mitigations

1.  Art direction iteration takes >3 weeks. Common for first-time direction-lockers. Pad to 4–5 weeks. Don't move into Phase 1 with "mostly decided" — costs more downstream than the extra week now.

2.  Pixel artist quality below the SRPG bar. Highest-impact risk. Mitigate with paid test pieces before contract signing. Reference an SRPG-specific brief ("GBA FE level of detail with X-Y modifications") rather than generic pixel art.

3.  Scope creep on unit count. You don't need 5+5+1 if 4+4+1 makes the same pitch. Cut ally units first, then trim enemy variety before player variety.

4.  You become the integration bottleneck. When sprites land in Week 5–6, every track funnels into your hands. Front-load asset integration plumbing so integration is fast, not novel work, when assets arrive.

5.  Narrative procrastination. Since it's your weakest pillar, the temptation is to keep deferring. Either hire the writer early so deadlines come from outside, or block dedicated writing days.

What I'd Do This Week 1. Start art direction reference gathering tonight — build a Pinterest / PureRef board with 50+ pieces. 2. Write the world bible outline in parallel — 1 page is fine for v0. 3. Open shortlists for pixel artists (Twitter/X, ArtStation, Indian gamedev Discords). Aim for 5 candidates by end of week. 4. Draft the 60-min prototype user-journey doc next week. 5. Commission paid style tests from your top 2 candidates by end of Week 2. 6. Lock direction by end of Week 3 and sign the pixel artist contract Week 4. The first three weeks are what determine whether the whole project ships in 4 months or 7.